## Slide 1: Employer Review Update for TPSPB Annex to Paper 10 (Agenda item 8)

## Slide 2: Aim and Purpose of the Review
Purpose
To consider roles and responsibilities of the employer and administrator to review whether they remain appropriate, fit for purpose, value for money and will provide assurance over the effective governance and financial management of the scheme in the medium to long term and make recommendations as appropriate.
  Scope
  The review will consider:
  The split of responsibilities between the administrator, employers and teachers – specifically focusing on data, contributions, pension events and communications,
  The roles and responsibilities of employers – specifically how they can continue to support the effective governance and financial management of the scheme,
  How developments in technology can support a more streamlined and cost effective administration of the scheme.

## Slide 3: Progress to Date
Engagement Round One took place in January: 52 Employers (14 Local Authorities, 14 Independents, 11 MATS and Academies, 4 HE/FE and 9 Payroll providers) provided feedback based on two new potential models
TPAF and TPARG consulted as part of the review. In addition, Employer Groups including ISBA and LGA have also been involved in the organisation of Focus Groups
136 cost pro-formas have been received from employers to help build the business case, these were provided in response to awareness raising pieces in the TP Employer Bulletins and the EFA Academies Newsletter
  Cost pro-formas provide information about the employer’s sector, the number of teachers and the amount of time spent on key tasks.
Separate visits to employers in each sector have taken place specifically to discuss improvements to the assurance and End of Year Certificate processes.
Engagement Round Two took place in May: 33 Employers (9 Local Authorities, 11 Independents, 4 MATS and Academies, 9 HE/FE) provided feedback based on a preferred model (including changes to End of Year Certificate (EOYC) and assurance processes at a high level)

## Slide 4: Progress to Date
Met with other similar pension providers (NHS and SPPA) to understand how they engage with employers and whether there is anything we can learn from their approach – they have shown a common approach but TPS is ahead in terms of readiness
Death in Service payments have been removed from scope as Teachers’ Pensions are delivering this now in response to stakeholder feedback.
Project Board agreed to not pursue development and implementation of a varying levels of service solution
As a result of the review, Employee and Employer contribution amounts have been made compulsory on the MDC return.
Initial analysis has been done to closely review the effect of making contribution data compulsory on the Monthly Data Collection (MDC) return and understand the future need/use for the EOYC.
The NAO and Audit Committee have been contacted to gage position and comments with regards to EOYC.

## Slide 5: Key Findings
Employers were very keen to reduce the administrative burden on them and see MDC as a major factor in achieving this .
Feedback is that “relationship management with members” should be the province of TP where possible, 100% of those that we engaged with were in favour here.
Making contribution data compulsory on MDC are likely to streamline the assurance processes for employers, this is being examined further.
Providing the contribution information in this way could allow employer level reconciliation of contributions and service and salary to take place monthly, therefore increasing the quality of data held’, aiding the administration and the production of the resource accounts.

## Slide 6: Risk Management
  Robust Evaluation – detailed evaluation spreadsheet captures feedback from one to ones and Focus Groups
  Employer Awareness – bulletins and stakeholder groups providing updates
  Strong Business Case – 136 cost pro-formas received – modelling applied to provide overall costs and savings
  Employer confidence in TP – suite of products to reassure members that TP able to give their members the service they need. Outcome Measures support this.
  Employer confidence in solution – assurance work so employers confident that they will continue to meet their obligations (Data Protections issues etc)
  NAO approval – already made aware of the project, will share preferred model with them

## Slide 7: Next Steps
  Development of assurance/EOYC processes, to be shared with NAO
  Recommendations Paper early August
  New Project for implementation